## Worksheet
Startup Planning - Project Plan - Tracking View
Task ID | Task Description | Owner | Start Date | End Date | Status | % Complete | Risk Level (1-5)
T001 | Conduct Market Research & Competitor Analysis | Jane Doe | 2024-04-01 | 2024-04-15 | In Progress | 75% | 3
T002 | Define Product Vision & MVP Features | John Smith | 2024-04-15 | 2024-05-15 | In Progress | 60% | 4
T003 | Create Wireframes & UI/UX Design Prototype | Alice Johnson | 2024-05-16 | 2024-06-15 | Not Started | 0% | 3
T004 | Develop Core MVP Application (Frontend) | Robert Brown | 2024-06-16 | 2024-08-31 | Not Started | 0% | 5
T005 | Develop Backend API & Database Architecture | Lisa Wong | 2024-06-16 | 2024-08-31 | Not Started | 0% | 5
T006 | Conduct Internal Alpha Testing & Feedback Loop | Michael Clark | 2024-09-01 | 2024-10-15 | Not Started | 0% | 3
T007 | Prepare Marketing & Launch Campaign Strategy | Sophia Martinez | 2024-10-16 | 2024-11-30 | Not Started | 0% | 4
T008 | Finalize Legal & Compliance Documentation | Peter Lee | 2024-11-01 | 2024-12-31 | Not Started | 0% | 5
Total Project Duration: | [5 empty] | 2024-04-01 to 2024-12-31
Overall Progress: | [5 empty] | 8%