## Worksheet
Startup Planning - Weekly Project Plan
Task ID | Task Name | Owner | Start Date | End Date | Status | Budget (USD)
Week 1: Planning & Foundation (2024-04-01 – 2024-04-07)
WP1.1 | Define business model and value proposition | Jane Doe | 2024-04-01 | 2024-04-03 | In Progress | $5,500
WP1.2 | Conduct market research and competitor analysis | John Smith | 2024-04-01 | 2024-04-05 | To Do | $3,800
Week 2: Product Development (2024-04-08 – 2024-04-14)
WP2.1 | Design wireframes and user interface mockups | Alice Brown | 2024-04-08 | 2024-04-11 | In Progress | $6,200
WP2.2 | Develop MVP prototype (Phase 1) | Mike Johnson | 2024-04-10 | 2024-04-13 | To Do | $15,750
Week 3: Team & Funding (2024-04-15 – 2024-04-21)
WP3.1 | Recruit core development team members | Sarah Lee | 2024-04-15 | 2024-04-17 | In Progress | $8,900
WP3.2 | Pitch to investors; secure seed funding goal ($250K) | David Kim | 2024-04-16 | 2024-04-19 | To Do | $5,000
Week 4: Launch Preparation (2024-04-22 – 2024-04-28)
WP4.1 | Finalize product features and testing plan | Alice Brown | 2024-04-22 | 2024-04-25 | To Do | $7,300
WP4.2 | Prepare launch marketing campaign and landing page | Lisa Wang | 2024-04-23 | 2024-04-27 | To Do | $9,500
Total Project Budget: | [5 empty] | $71,950