## Worksheet
Startup Planning - Advanced Project Template
Template Type: Project Template ¦ Purpose: Startup Planning ¦ Style/Version: Advanced
Phase | Task Description | Responsible Team | Start Date | End Date | Status | Budget (USD)
Phase 1 | Idea Generation & Market Research | Founding Team | 2024-01-05 | 2024-01-19 | In Progress | $8,500
| Competitor Analysis & SWOT Review | Product Team | 2024-01-15 | 2024-01-31 | Completed | $6,750
| Define Core Value Proposition | Marketing & Strategy Team | 2024-01-25 | 2024-02-15 | In Progress | $7,300
Phase 2 | Business Model Canvas Development | Strategy & Finance Team | 2024-02-10 | 2024-03-15 | In Progress | $9,500
| Financial Projections (3-Year) | Finance Team | 2024-02-18 | 2024-04-30 | Delayed | $15,800
| Operational Plan & Process Mapping | Operations Team | 2024-03-15 | 2024-04-30 | In Progress | $7,650
| Risk Assessment & Mitigation Plan | Legal & Risk Team | 2024-03-25 | 2024-05-15 | In Progress | $6,900
Phase 3 | Prototype Development (MVP) | Engineering & Product Team | 2024-05-01 | 2024-10-31 | Delayed | $89,500
| User Testing & Feedback Integration | UX & QA Team | 2024-11-01 | 2025-03-31 | Not Started | $45,750
| Iterative Refinement & Finalization | Product Team | 2025-04-15 | 2025-06-30 | Not Started | $38,400
Phase 4 | Go-to-Market Strategy Development | Marketing & Sales Team | 2025-05-15 | 2025-07-31 | In Progress | $46,900
| Soft Launch & Initial Rollout (Regional) | Launch Team | 2025-08-15 | 2026-01-31 | Not Started | $74,850
Total Project Budget: | [5 empty] | $392,850