## Worksheet
Startup Planning - Project Template - Analysis View
Phase | Activity/Component | Description | Owner | Status | Timeline (Start - End) | Budget Estimate ($)
Market Analysis & Validation
1.1 | Market Research | Conduct primary and secondary research on target market size, trends, customer needs. | Product Manager | In Progress | 2024-04-01 - 2024-05-15 | 8,500
1.2 | Competitive Analysis | Analyze direct and indirect competitors, their strengths, weaknesses, and market positioning. | Marketing Lead | Pending | 2024-05-16 - 2024-06-15 | 6,750
1.3 | User Persona Development | Create detailed buyer personas based on research data. | UX Researcher | Pending | 2024-06-16 - 2024-07-05 | 3,250
Product Development & MVP Planning
2.1 | MVP Feature Definition | Define core features for Minimum Viable Product based on market needs. | Product Manager | In Progress | 2024-07-06 - 2024-07-31 | 5,500
2.2 | Wireframing & Prototyping | Create low-fidelity wireframes and interactive prototypes for user testing. | UI/UX Designer | Pending | 2024-08-01 - 2024-09-15 | 9,800
2.3 | MVP Development (Tech) | Develop core functionality of MVP with backend and frontend components. | Lead Developer | Pending | 2024-09-16 - 2025-01-31 | 85,000
Business Model & Financial Planning
3.1 | Revenue Model Design | Define pricing strategy, monetization channels, and revenue streams. | Finance Lead | Pending | 2024-07-06 - 2024-08-15 | 4,500
3.2 | Financial Projections (3-Year) | Create detailed income statements, cash flow forecasts, and balance sheets. | Finance Lead | Pending | 2024-08-16 - 2024-09-30 | 7,250
Go-to-Market Strategy & Launch Planning
4.1 | Marketing & Sales Plan | Outline customer acquisition strategy, channels, and sales funnel. | Marketing Lead | Pending | 2024-10-01 - 2024-11-30 | 15,750
4.2 | Launch Event & Campaign Setup | Create launch campaign calendar, press release, and event logistics. | Marketing Coordinator | Pending | 2024-12-01 - 2025-01-31 | 18,500
Team & Operations Setup
5.1 | Talent Acquisition Plan | Define key roles, hiring timeline, and onboarding process. | HR Manager | Pending | 2024-07-15 - 2024-11-30 | 12,500
5.2 | Operational Infrastructure Setup | Set up tools, legal structure, and internal processes (HR, finance). | CFO & Operations Lead | Pending | 2024-08-15 - 2024-11-30 | 9,750
Total Estimated Budget: | [5 empty] | 218,800
Note:This template is designed for startup planning and analysis purposes. All timelines, budgets, and responsibilities are subject to adjustment based on project progress and external factors. Use this as a living document for strategic decision-making.