## Worksheet
Startup Planning - Project Template
Phase | Task/Activity | Responsible Team Member(s) | Status | Start Date | Due Date
Phase 1: Ideation & Concept Validation
1.1 | Market Research and Industry Analysis | Product Manager, Market Analyst | In Progress | 2025-04-01 | 2025-04-15
1.2 | Customer Persona Development | Marketing Lead, UX Designer | Pending | 2025-04-16 | 2025-04-30
1.3 | Competitive Analysis Report | Biz Development, Analysts | To Do | 2025-05-01 | 2025-05-10
Phase 2: Business Model Design
2.1 | Business Model Canvas Creation | CEO, COO, Product Lead | Pending | 2025-05-11 | 2025-05-20
2.2 | Revenue Model & Pricing Strategy | Finance Lead, Sales Director | To Do | 2025-05-21 | 2025-06-01
Phase 3: MVP Development
3.1 | Core Feature Definition | Product Owner, Tech Lead | Pending | 2025-06-02 | 2025-06-15
3.2 | MVP Design & Prototyping | UX/UI Team, Frontend Devs | To Do | 2025-06-16 | 2025-07-10
Phase 4: Fundraising & Legal
4.1 | Investor Pitch Deck Preparation | CEO, CFO, Marketing Lead | Pending | 2025-07-11 | 2025-07-31
4.2 | Licensing & Legal Documentation Setup | Legal Counsel, Admin Team | To Do | 2025-08-01 | 2025-08-15
Phase 5: Go-to-Market Strategy
5.1 | Marketing Campaign Planning | Marketing Team, PR Lead | Pending | 2025-08-16 | 2025-09-30
Final Milestone: Launch Readiness
6.1 | Full Project Review & Sign-Off | CEO, Project Manager, CTO | To Do | 2025-10-01 | 2025-10-15