## Worksheet
Startup Planning - Project Template (Client View)
Phase | Task | Description | Start Date | End Date | Status | Responsible Party
Phase 1: Ideation & Concept Validation | Market Research | Conduct in-depth analysis of target market, competitors, and customer needs. | 2024-04-01 | 2024-04-15 | In Progress | Marketing Team
| Concept Development | Create initial product/service concept and value proposition. | 2024-04-16 | 2024-04-30 | Pending | Product Team
| User Validation Session | Conduct focus groups and usability testing with target users. | 2024-05-01 | 2024-05-15 | Pending | Customer Experience Team
Phase 2: Business Model Design | Revenue Stream Analysis | Evaluate pricing models and potential revenue streams. | 2024-05-16 | 2024-05-31 | Pending | Finance Team
| Business Model Canvas Finalization | Develop and refine the complete business model canvas. | 2024-06-01 | 2024-06-15 | Pending | Strategy Team
| Investor Pitch Deck Creation | Prepare comprehensive pitch materials for potential investors. | 2024-06-16 | 2024-06-30 | Pending | Founders & Marketing Team
Phase 3: MVP Development | Prototype Design | Create wireframes and interactive prototypes. | 2024-07-01 | 2024-07-15 | Pending | Product & UX Team
| Core Feature Development | Build minimum viable product with essential functionality. | 2024-07-16 | 2024-08-15 | Pending | Engineering Team
| MVP Testing & Iteration | Conduct internal testing and gather feedback for improvements. | 2024-08-16 | 2024-08-31 | Pending | QA & Product Team
Phase 4: Launch Preparation | Go-to-Market Strategy | Develop launch plan with marketing, sales, and customer acquisition tactics. | 2024-09-01 | 2024-09-15 | Pending | Marketing & Sales Team
| Team Onboarding & Training | Prepare and train team members for launch operations. | 2024-09-16 | 2024-09-30 | Pending | Hiring & HR Team
| Launch Readiness Review | Conduct final review of all launch components and systems. | 2024-10-01 | 2024-10-05 | Pending | Executive Team
Template Version:Client View v1.0 ¦Last Updated:April 5, 2024