## Worksheet
Startup Planning - Project Template (Data Version)
Phase | Task Name | Responsible Person | Start Date | End Date | Status
Idea Validation | Market Research & Competitor Analysis | Product Manager | 2024-01-05 | 2024-01-19 | In Progress
Idea Validation | Customer Interviews (Target Audience) | Marketing Lead | 2024-01-12 | 2024-01-31 | Pending
Product Development | Create MVP Requirements Document | Product Owner | 2024-02-01 | 2024-02-15 | Pending
Product Development | UI/UX Design - Wireframes & Prototypes | UI/UX Designer | 2024-02-15 | 2024-03-15 | Pending
Product Development | Development - Frontend Implementation | Frontend Developer | 2024-03-16 | 2024-05-15 | Pending
Product Development | Development - Backend Implementation | Backend Developer | 2024-03-16 | 2024-05-15 | Pending
Testing & QA | User Acceptance Testing (UAT) | QA Lead | 2024-05-16 | 2024-06-15 | Pending
Testing & QA | Bug Fixing and Optimization | Full Stack Developer | 2024-06-16 | 2024-07-15 | Pending
Go-to-Market Strategy | Create Launch Marketing Plan | Marketing Manager | 2024-06-30 | 2024-07-31 | Pending
Go-to-Market Strategy | Launch Preparation & PR Outreach | PR Specialist | 2024-07-16 | 2024-08-15 | Pending
Total Duration: |  |  |  |  | From 2024-01-05 to 2024-08-15