## Worksheet
Startup Planning - Detailed Project Template
Project Overview
Field | Details | Field | Details | Field | Details
Name of Startup: |  | Industry/Domain: |  | Project Type: | Select TypeNew Product DevelopmentMarket ExpansionPlatform Build
Vision, Mission & Objectives
Company Vision:
Company Mission:
Goals & Key Performance Indicators
Goal Category | Specific Goal (SMART) | Target Date | KPI Metric | Baseline Value | Target Value
Sales & Revenue | Increase monthly recurring revenue by 25% within 6 months | 2024-10-31 | MRR (Monthly Recurring Revenue) | $10,000 | $12,500
User Acquisition | Reach 5,000 active users by Q4 2024 | 2024-12-31 | Total Active Users (MAU) | 1,500 | 5,000
Cash Flow Management | Maintain positive cash flow for 12 consecutive months starting Q3 2024
Team & Responsibilities
Role | Name (Optional) | Responsibilities | Experience Level | Status (Full-time/Part-time) | Notes
CEO | [Enter Name] | Overall strategy, fundraising, vision execution | 10+ years in tech startups | Full-time | Lead founder & decision maker
CFO/Finance Lead | [Enter Name] | Budgeting, financial planning, investor reporting | 7+ years in finance roles | Part-time (Contract) | Works with external auditors
CPO (Chief Product Officer) | [Enter Name] | Product roadmap, UX/UI direction | 8+ years in product management | Full-time | Handles sprint planning & backlog
Key Milestones & Timeline (Gantt-style)
Milestone | Start Date | End Date | Status | Owner(s) | Dependencies
Pitch Deck Finalized & Investor Ready | 2024-04-01 | 2024-05-15 | Completed | CEO, CPO | None (Initial Phase)
Minimum Viable Product (MVP) Launch | 2024-06-01 | 2024-11-30 | In Progress | CTO, Dev Team | Pitch deck approval, initial funding secured
Seed Funding Close & Investor Onboarding | 2024-10-01 | 2024-12-31 | Pending | CEO, CFO | MVP launch completed, traction data collected
First 1,000 Active Users Acquired | 2024-12-01 | 2025-03-31 | Not Started | Marketing Lead, CPO | MVP functionality confirmed & stable
Financial Forecast (Next 12 Months)
Month | Revenue (USD) | Operating Expenses (USD) | Net Profit/Loss (USD) | Cash Flow Forecast | Funding Required
Jan 2025 | $8,000 | $16,500 | -$8,500 | $42,356 (start) | Yes - $12K for Q1
Feb 2025 | $9,700 | $17,800 | -$8,100 | $34,256 (after expenses) | Yes - $15K for Q2
Mar 2025 | $13,400 | $18,900 | -$5,500 | $28,756 (after expenses) | Yes - $25K for Q3
Apr 2025 | $18,600 | $19,400 | -$800 | $27,956 (after expenses) | No (revenue increasing)
Risk Management & Contingency Planning
Risk Factor | Impact Level | Probability (Low/Med/High) | Mitigation Strategy | Owner & Status
Lack of Market Traction | High | Medium | Run targeted campaigns, gather early feedback, iterate on product features | Marketing Team - In Progress
Delayed MVP Development | High | High | Hire additional developers, break down tasks into sprints with weekly reviews, use agile methodology | CTO - In Progress
Funding Shortfall in Seed Round | Very High | Medium | Prepare backup pitch for angel investors; consider crowdfunding or grants as alternative funding sources | CEO - Monitoring Risk Level 2 (High)
Appendix: Supporting Documents & Links
• [Link to Pitch Deck] • [Link to Business Model Canvas] • [Link to Market Research Report] • [Link to Legal Structure Documentation]