## Worksheet
Startup Planning - Freelancer Project Template
Project Type: Freelancer ¦ Style/Version: Freelancer
Phase | Task Title | Description | Estimated Duration (Days) | Status
1. Discovery | Market Research & Validation | Analyze target market, competition, and demand for product/service. | 5-7 | Pending
1. Discovery | Business Model Design | Create revenue model, pricing strategy, and customer acquisition plan. | 3-5 | Pending
2. Planning | Startup Roadmap Development | Draft 6-month to 1-year strategic roadmap with milestones. | 7-10 | Pending
2. Planning | Funding Strategy & Pitch Deck | Develop pitch deck, funding goals, and investor outreach plan. | 5-8 | Pending
3. Execution | Team Building & Hiring Plan | Create roles and responsibilities; draft job descriptions for key hires. | 4-6 | Pending
3. Execution | Product/Service MVP Development | Outline features, design user flow, and begin prototyping. | 10-14 | Pending
4. Launch | Go-to-Market Strategy | Define launch plan, marketing channels, and early adopter engagement. | 5-7 | Pending
4. Launch | Landing Page & Branding Setup | Create website, logo, brand guidelines, and social media presence. | 3-5 | Pending
5. Growth | User Acquisition & Feedback Loop | Implement analytics tools; gather user feedback and iterate. | 7-10 | Pending
5. Growth | Metric Tracking & KPI Dashboard | Set up performance tracking for traffic, conversion, retention. | 3-5 | Pending