## Worksheet
Startup Planning - Project Template
Large Business Style ¦ Template Type: Project Template ¦ Purpose: Startup Planning
Project Overview & Key Milestones
Phase | Activity/Task | Responsible Team | Start Date | End Date | Status | Budget Allocation (USD)
1. Ideation & Validation | Market research, customer interviews, business model canvas | Product & Strategy Team | 2024-04-01 | 2024-05-15 | In Progress | $18,500
2. Product Development | Prototype creation, UX/UI design, MVP development | Engineering & Design Team | 2024-05-16 | 2024-08-31 | Pending | $175,000
3. Funding & Investor Engagement | Prepare pitch deck, investor outreach, fundraising rounds | Finance & Executive Team | 2024-06-01 | 2024-10-31 | Pending | $35,000
4. Market Launch Preparation | Go-to-market strategy, sales training, marketing campaign launch | Marketing & Sales Team | 2024-09-01 | 2024-11-30 | Pending | $87,500
5. Full Market Launch & Scaling | Official product release, customer onboarding, scaling operations | All Teams (Cross-functional) | 2024-12-01 | 2025-03-31 | Pending | $315,000
Financial Summary & Key Metrics
Metric | Target Value | Current Status | Variance (%)
Total Project Budget | $631,000 | $128,500 (20%) | 79.8%
Customer Acquisition Cost (CAC) | $55 | $61.32 | +11.5%
Monthly Recurring Revenue (MRR) | $80,000 | $24,756 | -69.1%
Time to First Revenue | 12 months | 9 months (planned) | -3 months