## Worksheet
Startup Planning - Project Template (Manager View)
Phase | Activity | Responsible Team | Start Date | End Date | Status
1. Concept & Ideation | Market research and idea validation | Product Team | 2023-10-01 | 2023-10-15 | In Progress
2. Business Model Design | Revenue model, KPIs, and go-to-market strategy | Business Development | 2023-10-16 | 2023-10-31 | To Do
3. Product Development | Prototype creation and user testing | R&D Team | 2023-11-01 | 2024-01-31 | To Do
4. Fundraising & Finance | Investor outreach, pitch deck, financial modeling | Finance & CEO Office | 2023-11-15 | 2024-02-15 | To Do
5. Team Building & Hiring | Recruit key roles, onboard team members | Hiring Manager & HR | 2023-11-01 | 2024-03-31 | To Do
6. Launch Preparation | Marketing campaign, customer onboarding plan | Marketing & Operations | 2024-01-15 | 2024-03-15 | To Do
7. Go-to-Market Launch | Official product launch and public release | Entire Team | 2024-03-16 | 2024-03-16 | To Do
Total Phases:7 ¦Completed:0 ¦In Progress:1 ¦On Hold:0