## Worksheet
Startup Planning - Monthly Project Template
Month | Objective | Key Activities | Responsible Person | Status | Progress (%) | Budget Allocated ($) | Budget Spent ($)
January | Market Research & Validation | Conduct customer interviews, analyze competitors, validate business model | Jane Doe | In Progress | 65% | $10,000 | $6,500
| Team Formation | Hire core team members (CTO, CMO) | John Smith | Pending Approval | 0% | $25,000 | $0
February - Product Development Phase
February | Prototype Development | Create MVP design and initial build | Sarah Lee | Completed | 100% | $45,000 | $45,200
| User Testing & Feedback Collection | Run usability tests with 25 target users | Mike Chen | In Progress | 40% | $8,000
March - Go-to-Market Strategy & Launch Preparation
March | Marketing Campaign Planning | Develop social media, email, and ad strategies | Lisa Park | Planned | 0%
| Pre-Launch Website & Landing Page | Build and deploy launch-ready website with sign-up forms | Alex Johnson | Pending Approval | 0%
| Beta Launch & Feedback Integration | Release to limited audience and collect feedback for final improvements | David Kim | Pending Start | 0%
Summary & Key Metrics (Monthly Overview)
Total Budget Allocated |  | $98,000
Total Budget Spent |  | $51,700
Average Progress Rate |  | 45%
This template is designed for monthly startup planning and project tracking. Update each month to reflect progress, budget usage, and upcoming goals.