## Worksheet
Startup Planning - Project Template (Office Use)
Project Overview & Key Milestones
Phase | Task Name | Responsible Team | Start Date | End Date | Status
Phase 1 - Ideation | Market Research & Needs Analysis | Product Team | 2024-04-01 | 2024-04-15 | In Progress
| Competitor Analysis & SWOT | Strategy Team | 2024-04-16 | 2024-05-01 | Pending
| Core Value Proposition Definition | Product & Marketing Team | 2024-05-02 | 2024-05-10 | Pending
Phase 2 - Planning | Business Model Canvas Development | Strategy & Finance Team | 2024-05-11 | 2024-05-31 | Pending
| Funding Strategy & Pitch Deck Creation | Finance & Executive Team | 2024-06-01 | 2024-06-15 | Pending
| Risk Assessment & Mitigation Plan | Operations & Legal Team | 2024-06-16 | 2024-06-30 | Pending
Phase 3 - Development | Prototype Design & Wireframing | Product & UX Team | 2024-07-01 | 2024-07-15 | Pending
| Core MVP Development (Sprint 1) | Engineering Team | 2024-07-16 | 2024-08-31 | Pending
| User Testing & Feedback Integration | Product & QA Team | 2024-09-01 | 2024-09-30 | Pending
Phase 4 - Launch | Go-to-Market Strategy Finalization | Marketing & Sales Team | 2024-10-01 | 2024-10-31 | Pending
| Initial Marketing Campaign Execution | Marketing Team | 2024-11-01 | 2024-11-30 | Pending
| Soft Launch & Performance Tracking | All Teams (Joint) | 2024-12-01 | 2024-12-31 | Pending
Total Estimated Duration: |  |  |  |  | 8 Months (2024-04-01 to 2024-12-31)
Note: This template is designed for internal office use. Update statuses regularly and share with stakeholders weekly.