## Worksheet
Startup Planning - One Page Project Template
Project Overview
Project Name: | InnovateX Startup Launch
Start Date: | 2024-04-01
End Date: | 2024-12-31
Status: | Planning Phase
Key Objectives
Objective 1: | Develop a minimum viable product (MVP) by Q3 2024
Objective 2: | Secure $500K in seed funding by Q4 2024
Objective 3: | Landing first 1,000 paying customers within the first year
Team & Responsibilities
CEO: | Jane Doe - Strategic planning, investor relations
CTO: | John Smith - Product development, tech stack management
CFO: | Alice Brown - Budgeting, financial forecasting
Marketing Lead: | Mike Johnson - Branding, digital marketing campaigns
Milestones & Timeline
Q2 2024: | Finalize business model, conduct market research
Q3 2024: | Develop MVP, begin user testing
Q4 2024: | Pitch to investors, launch beta version
Budget Summary
Development: | $180,000
Marketing & Sales: | $120,000
Team Salaries: | $200,000
Total Budget: | $500,000
Risk Assessment
Market Risk: | High competition; require unique value proposition
Technical Risk: | Potential delays in product development
Funding Risk: | Difficulty securing seed investment