## Worksheet
Startup Planning - Project Template
Phase | Task | Owner | Start Date | End Date | Status
Research & Ideation | Conduct market research and validate idea | [Assign Owner] | 2024-04-01 | 2024-04-15 | Pending
Business Model Design | Develop business model canvas and value proposition | [Assign Owner] | 2024-04-16 | 2024-04-30 | In Progress
Prototype Development | Create MVP prototype and test with users | [Assign Owner] | 2024-05-01 | 2024-05-15 | Not Started
Funding Strategy | Prepare pitch deck and identify investors | [Assign Owner] | 2024-05-16 | 2024-05-31 | Not Started
Legal & Registration | Register company and set up legal structure | [Assign Owner] | 2024-06-01 | 2024-06-15 | Not Started
Team Building | Hire core team and advisors | [Assign Owner] | 2024-06-16 | 2024-07-31 | Not Started
Go-to-Market Plan | Create marketing and launch strategy | [Assign Owner] | 2024-08-01 | 2024-08-31 | Not Started
Soft Launch | Launch to a small audience and collect feedback | [Assign Owner] | 2024-09-01 | 2024-10-15 | Not Started
Scale & Expand | Expand user base and grow operations | [Assign Owner] | 2024-10-16 | 2025-12-31 | Not Started
Total Duration: |  |  |  |  | Over 24 months
This template is for personal use. Customize as needed for your startup planning process.