## Worksheet
Startup Planning - Project Template (Planning View)
Phase | Task Name | Owner | Start Date | End Date | Status
Research & Discovery | Market Research and Validation | Jane Doe (Product Lead) | 2024-01-15 | 2024-02-15 | In Progress
Research & Discovery | Competitor Analysis | John Smith (Strategy) | 2024-01-20 | 2024-03-15 | Pending
Product Development | User Persona Creation | Sarah Lee (UX Designer) | 2024-02-01 | 2024-03-15 | In Progress
Product Development | Wireframing and Prototyping | Alex Chen (Frontend) | 2024-03-01 | 2024-05-15 | Pending
Marketing & Launch | Go-to-Market Strategy Development | Lisa Wang (Marketing) | 2024-04-01 | 2024-06-30 | Pending
Marketing & Launch | Pre-Launch Campaign Setup | Mike Johnson (Digital Marketing) | 2024-05-15 | 2024-07-31 | Pending
Funding & Finance | Investor Pitch Deck Preparation | David Brown (CEO) | 2024-01-30 | 2024-03-31 | In Progress
Funding & Finance | Fundraising Outreach and Meetings | Emily Davis (Business Development) | 2024-04-15 | 2024-08-31 | Pending
Total Duration: |  |  |  |  | 2024-08-31