## Worksheet
Startup Planning - Quarterly Project Template
Quarter | Objective/Goal | Milestones & Deliverables | Responsible Team Member(s) | Status | Notes/Comments
Q1 | Market Research & Validation | Competitor analysis, customer interviews (n=50), validate pain points, create initial persona profiles | Marketing & Product Team | Pending | Focus on target audience demographics and behavioral patterns.
Q1 | Prototype Development | Create MVP wireframes, conduct usability testing with 5 users, refine interface design | Product & Design Team | In Progress | Iterative feedback loop required.
Q2 | Funding Strategy & Pitch Preparation | Develop investor pitch deck, outline financial projections (3-year), identify 50 target investors | Finance & Executive Team | Pending | Include clear ROI and scalability metrics.
Q2 | Core Product Build Phase 1 | Develop backend infrastructure, build core features (v1.0), conduct internal QA testing | Engineering Team | In Progress | Milestone: Feature freeze by end of Q2.
Q3 | User Testing & Feedback Integration | Launch beta with 100 users, collect feedback, implement top 5 priority feature updates | Product & Customer Success Team | Pending | Track NPS and retention rate weekly.
Q3 | Go-to-Market Strategy Finalization | Craft marketing campaign plan, finalize pricing model, set up sales funnel | Marketing & Sales Team | Pending | Incorporate early user feedback into strategy.
Q4 | Product Launch & Initial Marketing Campaign | Official product launch, execute digital marketing push, onboard first 500 customers | Entire Team (Cross-functional) | Pending | Measure KPIs: conversion rate, CAC, LTV.
Q4 | Post-Launch Review & Planning for Q1 Next Year | Conduct retrospective meeting, analyze performance data, set initial goals for next cycle | Executive Team & Department Leads | Pending | Document lessons learned and best practices.
Note: This template is designed for quarterly startup planning. Update statuses weekly and review at the end of each quarter.