## Worksheet
Startup Planning - Project TemplateReport Version ¦ Template Type: Project Template
Phase | Task/Activity | Responsible Team/Person | Start Date | End Date | Status
I. Discovery & Ideation | Market Research & Validation | Product Team Lead, Market Analyst | 2024-01-05 | 2024-01-25 | In Progress
| Competitor Analysis Report | Competitive Intelligence Specialist | 2024-01-10 | 2024-01-30 | Pending Review
| Idea Brainstorming Workshop | Founding Team, Innovation Director | 2024-01-15 | 2024-01-17 | Completed
II. Business Model Development | Value Proposition Design | Product Manager, UX Designer | 2024-01-28 | 2024-02-15 | Pending Start
| Revenue Model Planning | Finance Lead, Business Strategist | 2024-01-30 | 2024-02-18 | Pending Start
| Customer Segmentation Strategy | Marketing Director, Data Analyst | 2024-01-31 | 2024-02-16 | Pending Start
III. Product & Technology Build | Prototype Development (MVP) | CTO, Engineering Team | 2024-02-19 | 2024-04-15 | Pending Start
| Technical Architecture Design | Lead Architect, DevOps Engineer | 2024-02-19 | 2024-03-15 | Pending Start
| Sprint Planning (Phase 1) | Scrum Master, Development Team | 2024-03-01 | 2024-03-15 | Pending Start
IV. Go-to-Market Strategy | Marketing Campaign Plan | Head of Marketing, Copywriter | 2024-04-16 | 2024-05-15 | Pending Start
| User Acquisition Strategy | Growth Hacking Lead, Analytics Team | 2024-04-16 | 2024-05-15 | Pending Start
| Partnership Outreach Plan | Biz Dev Manager, Legal Counsel | 2024-04-16 | 2024-05-15 | Pending Start
V. Funding & Financial Planning | Business Plan & Pitch Deck Finalization | CEO, CFO, Strategy Lead | 2024-05-16 | 2024-06-15 | Pending Start
| Funding Target & Investor List | CFO, Founder, Investor Relations Manager | 2024-05-16 | 2024-06-15 | Pending Start
| Fundraising Campaign Execution | CFO, Founder, VC Outreach Team | 2024-06-16 | 2024-07-31 | Pending Start
Total Duration: |  |  |  |  | 6 months (Jan 2024 - Jun 2024)
Note:This is a dynamic project template. Update status, dates, and responsibilities as the project progresses.
Last Updated: June 5, 2024