## Worksheet
Startup Planning - Project Template
Template Type:Project Template ¦Style/Version:Summary View
Project Phase | Key Activities | Owner | Start Date | End Date | Status
Market Research | Conduct customer interviews, analyze competitors, define target audience. | Jane Doe (Product Manager) | 2024-04-01 | 2024-04-15 | In Progress
Business Model Design | Develop value proposition, revenue streams, cost structure. | John Smith (CEO) | 2024-04-16 | 2024-04-30 | Pending
Product Development | Create MVP, UI/UX design, prototype testing. | Mike Lee (CTO) | 2024-05-01 | 2024-06-30 | Pending
Funding Strategy | Prepare pitch deck, identify investors, draft funding proposal. | Sarah Chen (CFO) | 2024-05-15 | 2024-06-15 | Pending
Go-to-Market Plan | Develop marketing strategy, sales funnel, launch timeline. | Lisa Brown (Marketing Lead) | 2024-06-16 | 2024-07-15 | Pending
Team Hiring & Onboarding | Recruit key team members, onboard new hires. | Tom Wilson (HR Manager) | 2024-05-10 | 2024-07-31 | Pending
Overall Project Summary
Total Duration: |  | 10 weeks (from 2024-04-01 to 2024-07-31)
Current Phase: |  | Market Research
On Track: |  | Yes (85% completion)