## Worksheet
Startup Planning - Project Timeline
Advanced Template ¦ Version 2.0 ¦ Updated: April 5, 2025
Phase / Milestone | Start Date | End Date | Duration (Days) | Status | Responsible Team
Phase 1: Ideation & Market Research | 2025-04-05 | 2025-04-19 | 15 | In Progress | Product Team
Phase 2: Business Model & Revenue Strategy | 2025-04-19 | 2025-05-03 | 14 | Pending | Strategy & Finance
Phase 3: MVP UI/UX Design & Prototyping | 2025-05-04 | 2025-05-18 | 15 | Pending | Design Team
Phase 4: Backend & Frontend Development | 2025-05-19 | 2025-06-30 | 43 | Pending | Engineering Team
Phase 5: Quality Assurance & Beta Testing | 2025-07-01 | 2025-07-14 | 14 | Pending | QA Team & Beta Users
Phase 6: Go-to-Market Strategy & Pre-Launch Campaigns | 2025-07-15 | 2025-07-31 | 17 | Pending | Marketing & Sales Team
Phase 7: Product Launch & Public Release | 2025-08-01 | 2025-08-01 | 1 | Pending | All Teams
Phase 8: Performance Analysis & Iteration Planning | 2025-08-02 | 2025-08-15 | 14 | Pending | Product & Analytics Team