## Worksheet
Annual Project Timeline - Startup Planning
Quarter | Phase | Key Activities | Milestones & Deliverables | Responsible Team | Status (Q1)
Q1 | Planning & Research Phase
| Market Research & Validation | Conduct surveys, focus groups, and competitor analysis; validate problem-solution fit. | Completed market validation report; validated target customer profile. | Product Team + Marketing | In Progress
| Business Model Design | Define revenue model, pricing strategy, and go-to-market approach. | Briefing document on business model canvas; MVP roadmap drafted. | Founder + Finance Team | To-Do
Q2 | Product Development Phase
| Prototype Development | Build and test MVP prototype with core features. | MVP prototype version 1.0 released; user feedback collected. | Engineering Team + UX/UI Design | In Progress
| Technical Architecture Setup | Establish cloud infrastructure, data security protocols, and deployment pipeline. | Cloud environment live; CI/CD pipeline operational. | DevOps + Security Team | To-Do
Q3 | Testing & Pre-Launch Phase
| User Testing & Feedback Integration | Run beta testing with 100 target users; iterate based on feedback. | Finalized feature set; bug resolution report completed. | Product Team + QA | In Progress
| Marketing & Sales Prep | Develop brand identity, website, launch campaign materials, and sales playbook. | Landing page live; initial email list of 500 leads acquired. | Marketing + Sales Team | To-Do
Q4 | Launch & Growth Phase
| Product Launch | Official public launch with initial feature set. | Product live on app stores/website; first 1,000 users acquired. | All Teams | To-Do
| Growth & Feedback Loop | Implement analytics tracking; collect user feedback and plan v1.1 roadmap. | Monthly retention report; 3 new feature requests prioritized. | Product + Marketing Team | To-Do
Total Duration (Annual) |  | 12 Months - Q1 to Q4
Note: This timeline is subject to change based on feedback, funding, or market conditions.