## Worksheet
Task | Start Date | End Date | Responsible | Status
Market Research & Validation | 2024-01-05 | 2024-01-31 | Product Team | In Progress
Business Model Development | 2024-02-01 | 2024-02-15 | CEO & Co-founder | Pending
Prototype Design (MVP) | 2024-02-16 | 2024-03-15 | Design & Dev Team | Pending
Initial Funding Round (Seed) | 2024-03-16 | 2024-04-30 | CEO & Investor Relations | Pending
Early User Testing (Beta) | 2024-05-01 | 2024-06-15 | Product & QA Team | Pending
Full Product Launch | 2024-06-16 | 2024-06-30 | Marketing & Operations | Pending