## Worksheet
Startup Planning - Project Timeline
Business Use Template ¦ Version 1.0
Phase/Task | Start Date | End Date | Status | Responsible Team Member(s) | Milestones & Deliverables
1. Ideation & Concept Validation | 2024-03-01 | 2024-03-15 | In Progress | CEO, Product Manager | Market research report, MVP concept document, customer feedback summary
2. Business Model Development | 2024-03-16 | 2024-03-31 | Pending | CFO, COO, Lead Strategist | Business model canvas, revenue forecast (Year 1–3), funding strategy draft
3. MVP Design & Prototyping | 2024-04-01 | 2024-05-15 | Pending | Design Team, Frontend Developers | User interface mockups, clickable prototype, usability testing report
4. Funding & Investor Outreach | 2024-05-16 | 2024-06-30 | Pending | CFO, CEO, Business Development Lead | Investor pitch deck, term sheet negotiations, seed funding secured (target: $500k)
5. Core Team Recruitment | 2024-06-15 | 2024-07-31 | Pending | HR Manager, CTO, CEO | Hired key roles: CTO, Lead Engineer, Marketing Director, Sales Lead
6. MVP Development & Testing | 2024-08-01 | 2024-11-30 | Pending | Engineering Team, QA Specialists | Fully functional MVP, internal beta testing completed, security audit report
7. Pre-Launch Marketing Campaign | 2024-10-01 | 2024-12-31 | Pending | Marketing Team, Community Manager | Email list (5k+), social media presence established, early adopter program launched
8. Official Launch & Customer Onboarding | 2025-01-01 | 2025-01-31 | Pending | All Teams, Support Team | Public launch event, first 500 customers onboarded, customer feedback system live
© 2024 Startup Planning Template ¦ Confidential Business Use Only