## Worksheet
Startup Planning - Project Timeline
Client View ¦ Updated: October 5, 2023
Phase | Task Name | Start Date | End Date | Status | Responsible Team
Phase 1: Discovery & Research | Market Analysis and Competitor Research | 2023-10-05 | 2023-10-19 | Ongoing | Product Team
| User Persona Development | 2023-10-16 | 2023-10-26 | Upcoming | UX Researcher
| Initial Business Model Canvas | 2023-10-19 | 2023-10-31 | Upcoming | CEO & Strategy Team
Phase 2: MVP Development | Wireframing & UI Design | 2023-11-01 | 2023-11-15 | Upcoming | Design Team
| Frontend Development (Core Features) | 2023-11-06 | 2023-11-30 | Upcoming | Frontend Devs
| Backend API Development | 2023-11-08 | 2023-12-15 | Upcoming | Backend Team
| MVP Integration & Testing | 2023-12-01 | 2023-12-31 | Upcoming | QA Team & Devs
Phase 3: Launch Preparation | Final QA & Security Audit | 2024-01-01 | 2024-01-15 | Upcoming | QA & Security Team
| Marketing Campaign Setup | 2024-01-08 | 2024-01-31 | Upcoming | Marketing Team
| Landing Page & Onboarding Flow Finalization | 2024-01-15 | 2024-01-31 | Upcoming | Design & Dev Team
Phase 4: Go Live | Soft Launch (Beta Users) | 2024-02-01 | 2024-02-15 | Upcoming | All Teams
| Public Launch & Go-to-Market Campaign | 2024-02-16 | 2024-03-31 | Upcoming | Marketing & Product Team