## Worksheet
Phase | Key Activities | Start Date | End Date | Responsible
Idea Validation | Market research, customer interviews, concept testing | 2024-01-01 | 2024-01-31 | Founder
Business Model | Define value proposition, revenue streams, customer segments | 2024-02-01 | 2024-02-15 | Founder & CTO
Prototype Development | Build MVP, conduct internal testing | 2024-02-16 | 2024-03-31 | CTO & Dev Team
User Testing | Collect feedback, iterate on design and features | 2024-04-01 | 2024-04-30 | Product Manager
Funding Preparation | Develop pitch deck, financial projections, investor outreach | 2024-05-01 | 2024-05-31 | Founder & CFO
Launch Readiness | Finalize product, set up marketing channels, prepare support systems | 2024-06-01 | 2024-06-30 | CEO & Marketing Lead