## Worksheet
Date | Activity | Responsible | Status | Notes
2023-10-01 | Define project scope and objectives | CEO & Team Lead | In Progress | Initial brainstorming session held.
2023-10-02 | Develop market research plan | Marketing Manager | Not Started | Research outline to be finalized by end of day.
2023-10-03 | Create initial business model canvas | Product Lead | In Progress
Next Week's Goals (Oct 4–Oct 8)
2023-10-04 | Conduct customer interviews | Customer Success Team | Not Started | Schedule initial 5 sessions.
Additional Notes and Updates (Daily)
2023-10-04 | Finalize MVP feature list | Product Manager | Not Started | To be reviewed with developers on Oct 5.
Daily Check-In Summary (Oct 1–Oct 4)
2023-10-04 | Daily stand-up meeting | All Team Members | Completed