## Worksheet
Startup Planning - Project Timeline Dashboard
Phase | Task Name | Start Date | End Date | Status | Owner
I. Ideation & Validation | Market Research & Problem Identification | 2024-05-15 | 2024-05-31 | In Progress | Marketing Team
| User Persona Development | 2024-06-01 | 2024-06-15 | Pending | Product Manager
| Competitor Analysis | 2024-06-16 | 2024-06-30 | Pending | Product Team
II. Product Development | Prototype Design & Wireframing | 2024-07-01 | 2024-07-15 | Pending | UX/UI Team
| Core Feature Development (MVP) | 2024-07-16 | 2024-08-31 | Pending | Engineering Team
| Backend Infrastructure Setup | 2024-07-16 | 2024-08-15 | Pending | DevOps Team
| User Testing & Feedback Integration | 2024-09-01 | 2024-09-30 | Pending | QA Team
III. Pre-Launch & Marketing | Landing Page Development & SEO Setup | 2024-10-01 | 2024-10-15 | Pending | Marketing Team
| Pilot Campaign & Early User Acquisition | 2024-10-16 | 2024-11-30 | Pending | Marketing Team
| PR & Media Outreach Plan | 2024-11-01 | 2024-11-30 | Pending | PR Team
IV. Launch & Scale | Official Product Launch (v1.0) | 2024-12-01 | 2024-12-31 | Pending | Exec Team
| Post-Launch Analytics & KPI Tracking Setup | 2025-01-01 | 2025-01-31 | Pending | Data Analytics Team
| Scaling Infrastructure & Hiring Plan Finalization | 2025-01-01 | 2025-03-31 | Pending | HR & Engineering Teams
Total Project Duration: |  |  | 2024-05-15 to 2025-03-31 | ~10 months