## Worksheet
Phase | Task | Start Date | End Date | Status | Responsible Team
Phase 1: Concept & Validation | Market Research & Analysis | 2024-01-05 | 2024-01-25 | In Progress | Product Team
| User Persona Development | 2024-01-15 | 2024-01-31 | In Progress | Marketing Team
| Ideation & Concept Finalization | 2024-01-26 | 2024-01-31 | Not Started | Innovation Team
Phase 2: Product Development | Wireframing & UX Design | 2024-02-01 | 2024-03-15 | Not Started | Design Team
| Prototype Development (MVP) | 2024-03-16 | 2024-05-31 | Not Started | Engineering Team
| User Testing & Feedback Integration | 2024-06-01 | 2024-07-15 | Not Started | Product & QA Team
| MVP Finalization & Internal Review | 2024-07-16 | 2024-08-15 | Not Started | R&D Team
Phase 3: Go-to-Market | Go-to-Market Strategy & Pricing Model | 2024-08-16 | 2024-09-15 | Not Started | Marketing & Sales Team
| Launch Campaign Development (Digital & PR) | 2024-09-16 | 2024-10-31 | Not Started | Creative Team
| Official Product Launch & Customer Onboarding | 2024-11-01 | 2024-11-30 | Not Started | All Teams
Phase 4: Post-Launch & Growth | Performance Monitoring & Analytics Setup | 2024-11-01 | 2024-12-31 | Not Started | Data Analytics Team
| User Feedback Collection & Feature Roadmap Planning | 2025-01-01 | 2025-03-31 | Not Started | Product Team & Customers
| Growth Strategy Implementation (Scaling) | 2025-04-01 | 2025-12-31 | Not Started | Business Development Team
Total Duration: 18 months (Jan 2024 - Dec 2025)