## Worksheet
Startup Planning - Project Timeline (Detailed)
Phase | Task / Milestone | Start Date | End Date | Status | Description / Notes
Phase 1: Ideation & Market Research | Define Core Value Proposition | 2025-04-01 | 2025-04-15 | In Progress | Craft a compelling USP based on market gaps and customer needs.
| Conduct Competitive Analysis (3 major players) | 2025-04-16 | 2025-04-30 | Pending | Analyze features, pricing, and customer reviews of key competitors.
| Perform Target Customer Surveys (n=150) | 2025-05-01 | 2025-05-14 | Pending | Use online platforms to gather qualitative and quantitative feedback.
| Finalize Business Concept & Validation Report | 2025-05-15 | 2025-05-31 | Pending | Compile insights into a validated startup concept document.
Phase 2: Business Foundation | Develop Legal Structure & Register Company | 2025-06-01 | 2025-06-30 | Pending | Select entity type (LLC/S-Corp), file with state, obtain EIN.
| Create Brand Identity & Logo Design | 2025-06-01 | 2025-06-15 | Pending | Define brand voice, colors, typography, and design assets.
| Secure Domain & Set Up Basic Website | 2025-06-16 | 2025-07-15 | Pending | Register domain, hosting setup, basic landing page with contact form.
| Develop Initial Business Plan & Pitch Deck | 2025-07-16 | 2025-08-14 | Pending | Create detailed plan covering product, market, team, financials, and funding needs.
Phase 3: Product Development | Design MVP Wireframes & UX Flows | 2025-08-15 | 2025-09-14 | Pending | Create clickable prototypes for core user journeys.
| Build Minimum Viable Product (MVP) | 2025-09-15 | 2026-01-31 | Pending | Develop core features with focus on usability and feedback collection.
| Internal Beta Testing (Team & Stakeholders) | 2026-02-01 | 2026-03-15 | Pending | Gather feedback on functionality, performance, and user experience.
| External Alpha Testing (Selected Users - n=50) | 2026-03-16 | 2026-04-30 | Pending | Release to early adopters; collect real-world usage data.
| Finalize Product Release Version (v1.0) | 2026-05-01 | 2026-05-31 | Pending | Address feedback, fix bugs, and prepare for public launch.
Phase 4: Go-to-Market & Launch | Develop Marketing Campaign Strategy | 2026-06-01 | 2026-06-30 | Pending | Create content calendar, social media plans, and outreach strategy.
| Set Up Sales Funnel & CRM Integration | 2026-07-01 | 2026-07-31 | Pending | Implement tools for lead capture, tracking, and customer onboarding.
| Pre-Launch Community Building (Social & Email) | 2026-08-01 | 2026-08-31 | Pending | Grow waitlist and social following through content and incentives.
| Official Product Launch Event & Public Release | 2026-09-01 | 2026-09-30 | Pending | Celebrate launch with press, influencers, and early customers.
Phase 5: Post-Launch Growth & Evaluation | Monitor KPIs & User Feedback (First 90 Days) | 2026-10-01 | 2027-01-31 | Pending | Track retention, engagement, support tickets, and feature requests.
| Plan Iteration Roadmap (v1.1 - v2.0) | 2027-02-01 | 2027-03-31 | Pending | Determine next feature set based on data and user input.
| Conduct Post-Launch Review & Lessons Learned Session | 2027-04-01 | 2027-04-15 | Pending | Evaluate what worked, what didn’t, and document insights.