## Worksheet
Startup Planning - Project Timeline (Employee View)
Task ID | Task Name | Description | Assignee | Start Date | Due Date | Status
T001 | Market Research & Analysis | Conduct competitor analysis and target audience research. | Jane Doe | 2023-10-01 | 2023-10-15 | In Progress
T002 | Business Model Development | Create and refine the business model canvas. | John Smith | 2023-10-16 | 2023-10-31 | Pending
T003 | Product Design & Prototyping | Design initial product mockups and develop prototype. | Alice Johnson | 2023-11-01 | 2023-11-30 | Pending
T004 | Funding Proposal Drafting | Prepare pitch deck and funding proposal document. | Robert Brown | 2023-11-15 | 2023-12-05 | Pending
T005 | Legal Structure Setup | Register business entity and finalize legal documentation. | Linda White | 2023-11-20 | 2023-12-15 | Pending
T006 | Team Recruitment Drive | Post job openings and begin candidate screening. | Mike Taylor | 2023-12-01 | 2024-01-15 | Pending
T007 | First Customer Pilot Launch | Deploy product to initial group of beta users. | Sarah Wilson | 2024-01-16 | 2024-03-15 | Pending
Last updated on October 5, 2023 ¦ Employee View - Project Timeline Template