## Worksheet
Startup Planning - Project Timeline (Extended)
Phase | Task/Activity | Owner | Start Date | End Date | Status | Priority
Phase 1: Ideation & Market Research (Weeks 1-4)
1 | Define core problem and target audience | Jane Doe (CEO) | 2023-10-02 | 2023-10-15 | In Progress | High
1.5 | Milestone: Finalize Problem Statement & Persona Drafts (Review) | Jane Doe (CEO) | 2023-10-16 | 2023-10-24 | Pending | High
1.8 | Competitor analysis & SWOT review | Mike Smith (Product) | 2023-10-16 | 2023-10-30 | In Progress | Medium
Phase 2: Business Model & MVP Design (Weeks 5-8)
2 | Develop business model canvas | Jane Doe (CEO), Laura Brown (Finance) | 2023-10-31 | 2023-11-14 | Pending | High
2.5 | Milestone: Business Model Approval & Budget Forecast Finalized (Board Review) | Jane Doe (CEO) | 2023-11-15 | 2023-11-24 | Pending | High
2.7 | Milestone: MVP Design & Wireframes Completed (UX Review) | Mike Smith (Product), Sarah Lee (Design) | 2023-11-15 | 2023-11-30 | Pending | High
Phase 3: Team & Legal Setup (Weeks 9-12)
3 | Recruit key team members (CTO, Marketing Lead) | Jane Doe (CEO), Laura Brown (HR) | 2023-12-01 | 2023-12-15 | Pending | High
3.5 | Milestone: Full Team Onboarded & Initial Roles Confirmed (Team Kickoff) | Jane Doe (CEO) | 2023-12-16 | 2023-12-31 | Pending | High
3.8 | Milestone: Legal Structure & IP Registration Completed (Legal Review) | Laura Brown (Finance), Alex Johnson (Legal) | 2023-12-16 | 2024-01-07 | Pending | High
Phase 4: MVP Development (Weeks 13-20)
4 | Set up development environment & version control | Tom Wilson (CTO) | 2024-01-08 | 2024-01-15 | Pending | High
4.5 | Milestone: MVP Core Features Built (Dev Sprint Review) | Tom Wilson (CTO) | 2024-01-16 | 2024-01-31 | Pending | High
4.8 | Milestone: MVP Beta Test (Internal & Pilot Users) | Mike Smith (Product), Sarah Lee (Design) | 2024-02-01 | 2024-03-15 | Pending | High
Phase 5: Pre-Launch Marketing (Weeks 21-24)
5 | Create landing page & content assets | Sarah Lee (Design), Mark Reed (Marketing) | 2024-03-16 | 2024-03-31 | Pending | Medium
5.5 | Milestone: Pre-Launch Campaign Launch (Email, Social, Ads) | Mark Reed (Marketing) | 2024-04-01 | 2024-04-30 | Pending | High
Phase 6: Launch & Post-Launch (Weeks 25-30)
6 | Finalize product launch plan & go-to-market strategy | Jane Doe (CEO), Mark Reed (Marketing) | 2024-05-01 | 2024-05-15 | Pending | High
6.5 | Milestone: Official Product Launch (Live Release) | Jane Doe (CEO) | 2024-05-16 |  | Pending | High
Post-Launch: Review & Next Steps (Weeks 31-32)
7 | Collect user feedback & performance metrics | Mike Smith (Product), Tom Wilson (CTO) | 2024-05-17 - 2024-05-31 |  | Pending | Medium
7.5 | Milestone: Post-Launch Review & Roadmap Planning Meeting (Leadership) | Jane Doe (CEO) | 2024-06-01 |  | Pending | High
Note:This timeline is based on a standard 32-week startup planning cycle. All dates are subject to change based on team availability and milestone reviews.