## Worksheet
Startup Planning - Project Timeline (Freelancer Style)
Phase | Task Description | Start Date | End Date | Status | Owner
I. Discovery & Ideation
1. Market Research | Analyze target audience, competitors, and market gaps. | 2024-03-01 | 2024-03-15 | In Progress | Jane Doe
2. Idea Validation | Conduct surveys and interviews with potential users. | 2024-03-16 | 2024-03-31 | Pending | John Smith
II. Business Planning
3. Business Model Design | Create revenue model, pricing strategy, and value proposition. | 2024-04-01 | 2024-04-15 | In Progress | Jane Doe
4. Financial Projections | Develop 3-year P&L, cash flow, and break-even analysis. | 2024-04-16 | 2024-05-05 | Pending | Mike Chen
III. Product Development
5. MVP Design | Create wireframes, UX flows, and design mockups. | 2024-05-06 | 2024-06-15 | Pending | Alice Kim
6. Prototype Development | Build and test basic version of the product. | 2024-06-16 | 2024-07-31 | Pending | Carlos Ruiz
IV. Launch Preparation
7. Marketing Strategy | Develop branding, messaging, and launch campaign plan. | 2024-08-01 | 2024-08-31 | Pending | Sophie Brown
8. Legal & Compliance Setup | Register company, secure IP, and finalize terms. | 2024-09-01 | 2024-09-30 | Pending | Raj Patel
V. Go-to-Market & Scaling
9. Soft Launch | Release to a small user group with feedback collection. | 2024-10-01 | 2024-11-30 | Pending | Jane Doe, John Smith
10. Full Launch & Growth Campaigns | Official launch with digital marketing and user acquisition. | 2024-12-01 | 2025-03-31 | Pending | All Team Members
Total Estimated Timeline: |  |  |  |  | 12 Months (2024-03 to 2025-03)