## Worksheet
Startup Planning - Project Timeline (Home Use)
Phase | Task | Start Date | End Date | Status | Owner
Idea & Research | Define startup concept and mission statement | 2024-01-05 | 2024-01-15 | Pending | John Doe
Idea & Research | Conduct market research and competitor analysis | 2024-01-16 | 2024-01-31 | In Progress | Jane Smith
Business Planning | Develop business model canvas and value proposition | 2024-02-01 | 2024-02-15 | In Progress | John Doe
Business Planning | Create detailed business plan and financial projections | 2024-02-16 | 2024-03-15 | Pending | Jane Smith
Product Development | Build MVP (Minimum Viable Product) | 2024-03-16 | 2024-05-15 | Pending | Mike Johnson
Product Development | Test MVP with early users and collect feedback | 2024-05-16 | 2024-06-15 | Pending | Sarah Brown
Marketing & Launch | Develop marketing strategy and branding assets | 2024-06-16 | 2024-07-15 | Pending | Alex Lee
Marketing & Launch | Launch product and initiate public marketing campaign | 2024-07-16 | 2024-08-31 | Pending | Alex Lee
Growth & Scale | Monitor KPIs and user engagement post-launch | 2024-09-01 | 2024-11-30 | Pending | John Doe
Growth & Scale | Plan next round of product enhancements and scaling strategy | 2024-12-01 | 2025-01-31 | Pending | Jane Smith
Template for Home Use ¦ Startup Planning & Project Timeline ¦ Version 1.0