## Worksheet
Startup Planning - Project Timeline
Phase | Task Name | Start Date | End Date | Status | Responsible Team/Person
Pre-Development | Market Research & Feasibility Study | 2025-01-01 | 2025-01-31 | In Progress | Product Team, Market Analysts
| Business Model Design & Validation | 2025-02-01 | 2025-03-15 | Pending Approval | CEO, CFO, Strategy Lead
| Funding Proposal & Investor Outreach | 2025-03-16 | 2025-04-30 | Not Started | CFO, Investor Relations Team
Development Phase
Product Development | Core Architecture & Tech Stack Setup | 2025-05-01 | 2025-06-15 | In Progress | CTO, Engineering Team
| Feature Development (MVP) | 2025-06-16 | 2025-10-31 | In Progress | Engineering & UX Team
| User Testing & Feedback Integration | 2025-11-01 | 2025-11-30 | Not Started | QA Team, Product Managers
| Roadmap Finalization & Release Planning | 2025-12-01 | 2025-12-31 | Not Started | CPO, Product Team
Launch & Growth Phase
Go-To-Market Strategy | Branding & Identity Development | 2026-01-01 | 2026-01-31 | Not Started | Marketing Lead, Design Team
| Landing Page & Campaign Setup (Pre-Launch) | 2026-02-01 | 2026-03-31 | Not Started | Marketing Team, DevOps
| Main Product Launch & Initial Marketing Push | 2026-04-01 | 2026-04-30 | Not Started | CFO, CMO, Sales Team
Post-Launch & Optimization
Operations & Growth | Customer Onboarding Process Design | 2026-05-01 | 2026-05-31 | Not Started | CX Team, Support Lead
| KPI Tracking & Performance Analysis Setup | 2026-06-01 | 2026-06-30 | Not Started | Data Analytics Team, CRO
| Iterative Feature Rollouts & Scalability Planning | 2026-07-01 | Ongoing | Not Started | Engineering, Product, Ops Teams
Total Timeline Duration: |  | January 1, 2025 – December 31, 2026 (Approx. 24 months)
Prepared by: Startup Planning Office ¦ Last Updated: May 5, 2025