## Worksheet
Startup Planning - Project Timeline (Manager View)
Phase | Task | Start Date | End Date | Status | Owner | Budget (USD)
Pre-Planning | Define Vision & Mission | 2024-01-05 | 2024-01-15 | In Progress | Alice Chen | $5,000
| Market Research & Analysis | 2024-01-16 | 2024-01-31 | Pending | James Rodriguez | $7,500
| Competitor Benchmarking | 2024-02-01 | 2024-02-15 | Pending | Sophia Lee | $6,800
Development | Product Concept & Wireframes | 2024-02-16 | 2024-03-15 | Pending | Alex Kim | $15,000
| Prototype Development | 2024-03-16 | 2024-04-30 | Pending | Liam Patel | $35,000
| User Testing & Feedback Loop | 2024-05-01 | 2024-06-15 | Pending | Elena Martinez | $8,900
| Final Product Refinement | 2024-06-16 | 2024-07-31 | Pending | Alex Kim, Liam Patel | $18,500
Launch Preparation | Marketing Strategy & Campaign Design | 2024-08-01 | 2024-08-31 | Pending | Sophia Lee, James Rodriguez | $25,000
| Website & Sales Funnel Setup | 2024-09-01 | 2024-10-15 | Pending | Elena Martinez, Alice Chen | $38,750
Go-Live & Evaluation | Soft Launch & Beta Testing | 2024-10-16 | 2024-11-30 | Pending | All Team Leads | $7,500
Total Budget Estimate: | [5 empty] | $175,950