## Worksheet
Startup Planning - Project Timeline
Task ID | Task Name | Start Date | End Date | Status | Owner
T001 | Market Research & Validation | 2024-01-05 | 2024-01-19 | In Progress | Alice Johnson
T002 | Competitor Analysis | 2024-01-152024-01-31PendingRobert Lee
T003 | User Persona Development | 2024-01-252024-02-08In ProgressSarah Kim
T004 | Idea Refinement Workshop | 2024-01-312024-02-15Not StartedMarcus Taylor
Task ID | Task Name | Start Date | End Date | Status | Owner
T005 | Wireframe Creation (MVP) | 2024-02-162024-03-15In ProgressLisa Chen
T006 | Prototype Development (Frontend) | 2024-03-182024-04-15PendingDaniel Park
T007 | Backend Architecture Design | 2024-03-182024-04-15PendingAmina Hassan
T008 | User Testing (Prototype) | 2024-05-132024-05-31Not StartedSarah Kim
Task ID | Task Name | Start Date | End Date | Status | Owner
T009 | Marketing Strategy & Branding | 2024-06-152024-07-15PendingRobert Lee
T010 | Sales Funnel Setup (Landing Page) | 2024-06-302024-07-31Not StartedLisa Chen
T011 | Campaign Launch Planning (Social Media) | 2024-07-152024-08-31Not StartedAlice Johnson
T012 | Funding Pitch Deck Finalization | 2024-06-152024-07-31In ProgressMarcus Taylor
Task ID | Task Name | Start Date | End Date | Status | Owner
T013 | Main Product Launch (V1.0) | 2024-09-012024-09-30Not StartedAll Team Members
T014 | Customer Onboarding Program Setup | 2024-09-152024-10-31Not StartedDaniel Park
T015 | Data Collection & Feedback Loop (First Month) | 2024-10-012024-11-30Not StartedSarah Kim
T016 | V2.0 Roadmap Planning Session | 2024-11-152024-12-31Not StartedMarcus Taylor & Team Leads
Startup Planning - Project Timeline ¦ Prepared on: October 5, 2024 ¦ Confidential – For Internal Use Only