## Worksheet
Startup Planning - Project Timeline (Office Use)
Phase | Task | Start Date | End Date | Responsible Team/Person | Status
I. Ideation & Research | Market research and customer validation | 2023-10-01 | 2023-10-15 | Product Team / CEO | In Progress
| Competitor analysis and SWOT assessment | 2023-10-16 | 2023-10-31 | Business Development | Pending
II. Planning & Design | Define MVP features and roadmap | 2023-11-01 | 2023-11-15 | Product Team / CTO | Pending
| UI/UX wireframing and prototyping | 2023-11-16 | 2023-11-30 | Design Team | Pending
III. Development | Frontend development (MVP) | 2023-12-01 | 2024-01-15 | Development Team / CTO | Pending
| Backend infrastructure setup and API development | 2023-12-01 | 2024-01-31 | Engineering Team | Pending
IV. Testing & Validation | User testing with pilot group (beta release) | 2024-02-01 | 2024-02-15 | Product & QA Teams | Pending
| Iterate based on feedback and fix bugs | 2024-02-16 | 2024-03-15 | Development & Product Teams | Pending
V. Launch & Growth | Official product launch (public release) | 2024-03-16 | 2024-03-31 | Marketing & Sales Teams / CEO | Pending
| Initial marketing campaign and user acquisition | 2024-04-01 | 2024-06-30 | Marketing Team | Pending
Template Version: Office Use ¦ Last Updated: October 2023 ¦ Project Timeline for Startup Planning