## Worksheet
Startup Planning - Project Timeline
Phase | Task Description | Start Date | End Date | Status | Responsible Person
Market Research | Analyze target market and competitors. | 2024-01-05 | 2024-01-31 | In Progress | Jane Doe
Business Model Development | Create revenue streams and value proposition. | 2024-02-01 | 2024-02-15 | Status Pending | John Smith
Product Design & Prototyping | Design MVP and develop prototype. | 2024-02-16 | 2024-03-31 | Status Pending | Alex Brown
Funding Strategy | Prepare pitch deck and investor outreach plan. | 2024-03-15 | 2024-04-15 | Status Pending | Sarah Lee
Team Hiring | Recruit core team members (dev, marketing). | 2024-04-01 | 2024-05-15 | Status Pending | Marcus Green
Product Development (MVP) | Build and test minimum viable product. | 2024-05-16 | 2024-07-31 | Status Pending | Alex Brown
User Testing & Feedback | Conduct usability testing with early users. | 2024-08-01 | 2024-08-31 | Status Pending | Jane Doe
Launch Preparation | Finalize marketing, website, and launch plan. | 2024-09-01 | 2024-09-30 | Status Pending | Sarah Lee
Official Launch | Release product to public and announce. | 2024-10-01 | 2024-10-05 | Status Pending | All Team Members
Template Type: Project Timeline ¦ Purpose: Startup Planning ¦ Style/Version: Personal Use