## Worksheet
Startup Planning - Project Timeline (Planning View)
Phase | Task | Start Date | End Date | Status | Owner
Market Research & Validation | Conduct target market analysis | 2024-01-05 | 2024-01-15 | In Progress | Jane Smith
| Interview potential customers | 2024-01-16 | 2024-01-30 | Pending | John Doe
| Analyze competition landscape | 2024-01-18 | 2024-02-05 | Pending | Lisa Wong
Product Development | Create product roadmap | 2024-01-10 | 2024-01-31 | In Progress | Mark Johnson
| Build MVP prototype | 2024-02-01 | 2024-03-15 | Pending | Sarah Lee
| Test with early users | 2024-03-16 | 2024-04-15 | Pending | Daniel Kim
Business Model & Funding | Develop revenue model | 2024-01-20 | 2024-01-31 | In Progress | Lisa Wong
| Prepare pitch deck | 2024-02-01 | 2024-03-15 | Pending | Jane Smith
| Schedule investor meetings | 2024-03-16 | 2024-05-31 | Pending | John Doe
Team & Operations Setup | Hire core team members | 2024-01-30 | 2024-03-15 | Pending | Mark Johnson
| Set up office & tools | 2024-02-15 | 2024-03-15 | Pending | Sarah Lee
Key Milestones (Planned)
Milestone |  | Target Date | Actual Date | Status | Notes
Market Validation Complete |  | 2024-02-15 |  | Pending | Customer feedback collected and analyzed
MVP Ready for Testing |  | 2024-03-15 |  | Pending | Functional prototype delivered to testers
First Round Funding Secured |  | 2024-05-31 |  | Pending | Target $1.5M raised from angel investors