## Worksheet
Phase | Task | Start Date | End Date | Responsible Team | Status
1. Ideation & Research | Market Analysis & Competitor Research | 2024-01-05 | 2024-01-19 | Product Team | In Progress
| User Persona Development | 2024-01-20 | 2024-01-31 | Marketing Team | Pending
| Initial Concept Validation | 2024-02-01 | 2024-02-15 | R&D Team | Pending
2. Product Development | UI/UX Design Phase | 2024-02-16 | 2024-03-15 | Design Team | In Progress
| Core Feature Development | 2024-03-16 | 2024-05-31 | Development Team | Pending
| Internal Testing & Bug Fixes | 2024-06-01 | 2024-06-30 |  | Pending
3. Launch Preparation | Marketing Campaign Planning | 2024-05-15 | 2024-06-15 |  | Marketing & Sales Team | In Progress
| Customer Onboarding Workflow Setup | 2024-06-16 | 2024-07-15 | Pending
| Pre-Launch Beta Testing | 2024-07-16 | 2024-08-15 | Pending
4. Official Launch | Go-Live & Public Release | 2024-08-16 | 2024-08-16 | All Teams | Pending
Post-Launch Feedback Collection | 2024-08-17 | 2024-09-15 | In Progress
First Quarter Review & Iteration Planning | 2024-09-16 | 2024-09-30 | Pending