## Worksheet
Startup Planning - Project Timeline
Phase | Task | Start Date | End Date | Responsible Team | Status
Market Research & Validation
Phase 1 | Conduct Market Analysis | 2024-01-05 | 2024-01-25 | Product Team | Completed
Phase 1 | Identify Target Customer Segments | 2024-01-26 | 2024-02-15 | Marketing Team | Completed
Product Development
Phase 2 | Create MVP Requirements Document | 2024-02-16 | 2024-03-05 | Product Team | In Progress
Phase 2 | Design UI/UX Prototypes | 2024-03-06 | 2024-03-31 | Design Team | In Progress
Go-to-Market Strategy
Phase 3 | Develop Sales & Marketing Plan | 2024-04-01 | 2024-04-30 | Marketing Team | Delayed
Launch Preparation
Phase 4 | Finalize Legal & Compliance Documentation | 2024-05-01 | 2024-05-15 | Legal Team | Completed
Phase 4 | Set Up Infrastructure & Systems | 2024-05-16 | 2024-06-30 | IT Team | In Progress
Launch & Post-Launch
Phase 5 | Official Product Launch | 2024-07-01 | 2024-07-31 | Executive Team | Delayed
Phase 5 | Gather Customer Feedback & Iterate | 2024-08-01 | 2024-10-31 | Product & Support Teams | Pending