## Worksheet
Phase | Activity | Start Date | End Date | Status | Responsible Team/Person
Pre-Launch Preparation | Market Research & Analysis | 2024-01-01 | 2024-01-31 | In Progress | Product Team
| Business Model Finalization | 2024-02-01 | 2024-02-15 | In Progress | Strategy Team
| Fundraising Strategy Development | 2024-02-16 | 2024-03-15 | Pending | Finance & CEO Office
Product Development | Idea Prototyping & MVP Design | 2024-03-16 | 2024-04-30 | Pending | Engineering Team
| UI/UX Development & Testing | 2024-05-01 | 2024-06-15 | Pending | Design Team
| Backend & Infrastructure Setup | 2024-05-15 | 2024-07-31 | Pending | DevOps Team
| MVP Beta Testing (Internal) | 2024-08-01 | 2024-08-31 | Pending | QA & Product Team
Launch Preparation | Marketing Campaign Planning | 2024-07-01 | 2024-08-31 | Pending | Marketing Team
| PR & Media Outreach Initiation | 2024-08-15 | 2024-09-30 | Pending | Comms Team
| Launch Event Planning & Logistics | 2024-09-15 | 2024-10-15 | Pending | Operations Team
Go-Live & Post-Launch | Public Launch (MVP) | 2024-10-16 | 2024-10-16 | Pending | All Teams
| User Feedback Collection & Analysis | 2024-10-17 | 2024-11-30 | Pending | Product & Support Teams
| First Product Update Release (v1.1) | 2024-12-01 | 2024-12-31 | Pending | Engineering Team
Total Duration: |  | 2024-01-01 to 2024-12-31 (Approx. 1 year)
Notes:
Status values can be: Pending, In Progress, Completed.
This timeline is subject to review and adjustment based on stakeholder feedback and resource availability.
Update frequency: Monthly reviews with core leadership team.