## Worksheet
Phase | Task | Start Date | End Date | Responsible | Status
Idea Development | Define core concept and value proposition | 2024-01-05 | 2024-01-15 | Founder | Completed
Market Research | Conduct competitor analysis and target audience study | 2024-01-16 | 2024-01-31 | Marketing Lead | In Progress
Prototype Design | Create wireframes and MVP design mockups | 2024-02-01 | 2024-02-15 | Product Designer | Not Started
Development Phase | Build initial version of product | 2024-02-16 | 2024-03-31 | Development Team | Not Started
Beta Testing | Test product with selected users and gather feedback | 2024-04-01 | 2024-04-30 | QA Team | Not Started
Launch Preparation | Finalize marketing strategy and launch plan | 2024-05-01 | 2024-05-15 | Marketing & CEO | Not Started
Official Launch | Release product publicly and initiate campaigns | 2024-05-16 | 2024-05-16 | Entire Team | Not Started