## Worksheet
Startup Planning - Project Timeline (Small Business)
Phase | Milestone | Start Date | End Date | Status
Planning & Research | Market Analysis Complete | 2024-01-01 | 2024-01-31 | In Progress
Planning & Research | Business Model Finalized | 2024-02-01 | 2024-02-15 | Pending
Funding & Legal Setup | Startup Funding Secured | 2024-03-01 | 2024-03-31 | Pending
Funding & Legal Setup | Business Registration Complete | 2024-04-01 | 2024-04-15 | Pending
Product Development | MVP Prototype Ready | 2024-05-01 | 2024-06-30 | Pending
Product Development | MVP Testing Phase Complete | 2024-07-01 | 2024-08-15 | Pending
Marketing & Launch | Landing Page & Branding Live | 2024-08-16 | 2024-09-30 | Pending
Marketing & Launch | Soft Launch to Beta Users | 2024-10-01 | 2024-11-30 | Pending
Growth & Scaling | Full Product Launch | 2024-12-01 | 2024-12-31 | Pending
Growth & Scaling | First 6 Months Review & Strategy Update | 2025-01-01 | 2025-01-31 | Pending