## Worksheet
Startup Planning - Project Timeline
Phase | Task Description | Start Date | End Date | Status | Responsible Team/Person
1. Ideation & Validation | Market research and customer interviews | 2024-01-05 | 2024-01-25 | In Progress | Product Team & CEO
1. Ideation & Validation | Validate core value proposition | 2024-01-26 | 2024-02-05 | Pending | Marketing & UX Researcher
2. Business Model Design | Define revenue streams and pricing model | 2024-02-06 | 2024-02-15 | Pending | Finance & Strategy Team
2. Business Model Design | Create business model canvas | 2024-02-16 | 2024-02-19 | Pending | Creative Team & CEO
3. Product Development | Build MVP wireframes and prototypes | 2024-02-20 | 2024-03-15 | Pending | Design & Frontend Team
3. Product Development | Develop core features for MVP | 2024-03-16 | 2024-05-15 | Pending | Full Stack & Backend Team
4. Launch Preparation | Create go-to-market strategy and sales plan | 2024-05-16 | 2024-06-15 | Pending | Marketing & Sales Team
4. Launch Preparation | Set up customer onboarding flow and support system | 2024-06-16 | 2024-07-31 | Pending | Customer Success & DevOps Team
5. Official Launch | Launch MVP to early adopters | 2024-08-01 | 2024-08-31 | Pending | All Teams
6. Post-Launch Growth | Gather user feedback and iterate on product | 2024-09-01 | 2024-11-30 | Pending | Product & UX Teams