## Worksheet
Task | Start Date | End Date | Status | Responsible Party
Market Research & Validation | 2023-10-01 | 2023-10-15 | In Progress | Product Team
Business Model Design | 2023-10-16 | 2023-10-31 | Pending | CEO & CFO
Prototype Development | 2023-11-01 | 2023-12-15 | Pending | R&D Team
User Testing Phase 1 | 2023-12-16 | 2024-01-05 | Pending | Product Team
Refine Product & Roadmap | 2024-01-06 | 2024-01-20 | Pending | Product & Strategy Team
Funding Round Preparation | 2024-01-21 | 2024-02-15 | Pending | CFO & Business Development
Funding Pitch & Closing | 2024-02-16 | 2024-03-31 | Pending | CEO & CFO
Team Hiring & Onboarding | 2024-04-01 | 2024-05-31 | Pending | Hiring Team & HR
Full Product Launch (MVP) | 2024-06-01 | 2024-06-30 | Pending | All Teams