## Worksheet
Startup Planning - Project Timeline (Team Use)
Phase | Task | Owner | Start Date | End Date | Status
Phase 1: Ideation | Define core problem & target audience | Product Team | 2025-04-01 | 2025-04-07 | Pending
| Conduct market research & competitor analysis | Market Researcher | 2025-04-08 | 2025-04-15 | In Progress
| Develop initial value proposition & concept sketches | Design Team | 2025-04-16 | 2025-04-23 | Pending
Phase 2: Planning | Create business model canvas | Business Lead | 2025-04-24 | 2025-05-01 | In Progress
| Outline MVP features & roadmap | Product Manager | 2025-05-02 | 2025-05-16 | Pending
| Finalize team roles & responsibilities | HR Coordinator | 2025-05-17 | 2025-05-31 | Pending
Phase 3: Development | Design UI/UX mockups & prototypes | Lead Designer | 2025-06-01 | 2025-06-14 | Pending
| Develop MVP backend & frontend code | Engineering Team | 2025-06-15 | 2025-07-31 | Pending
| Internal testing & bug fixing | QA Team | 2025-08-01 | 2025-08-15 | Pending
Phase 4: Launch | Prepare marketing materials & campaign plan | Marketing Lead | 2025-08-16 | 2025-08-31 | Pending
| Launch MVP to early adopters | Product Team & Marketing | 2025-09-01 | 2025-09-30 | Pending
| Gather feedback & plan next iteration | Product & UX Team | 2025-10-01 | 2025-10-31 | Pending
This timeline is a living document. Updates to dates and statuses are shared weekly during team syncs.