## Worksheet
Startup Planning - Project Timeline
Phase | Task | Start Date | End Date | Status | Responsible Team Member(s)
Pre-Planning | Market Research & Feasibility Study | 2025-04-01 | 2025-04-15 | In Progress | Marketing Team, Product Lead
| Define Target Audience & Value Proposition | 2025-04-16 | 2025-04-30 | In Progress | Product Manager, UX Designer
| Create Business Model Canvas | 2025-05-01 | 2025-05-10 | Pending | CEO, Finance Lead
| Secure Initial Funding (Seed Round) | 2025-05-11 | 2025-06-30 | Pending | CFO, CEO, Investor Relations
Product Development | Define Product Requirements & MVP Scope | 2025-07-01 | 2025-07-15 | Pending | Product Manager, Engineering Lead
| UI/UX Design & Prototyping | 2025-07-16 | 2025-08-15 | Pending | UX Designer, Frontend Developer
| Backend & Frontend Development (MVP) | 2025-08-16 | 2025-11-30 | Pending | Full Stack Team, QA Lead
| MVP Testing & Feedback Collection | 2025-12-01 | 2025-12-31 | Pending | QA Team, Product Manager, Beta Users
Launch Preparation | Create Go-to-Market Strategy & Campaign Plan | 2026-01-01 | 2026-01-31 | Pending | Marketing Team, Sales Lead
| Build Sales & Support Infrastructure | 2026-02-01 | 2026-03-15 | Pending | Sales Team, Operations Lead
| Finalize Pricing & Packaging Models | 2026-03-16 | 2026-04-15 | Pending | CFO, Product Manager, Legal Team
| Launch Event & Public Release (MVP) | 2026-04-16 | 2026-04-16 | Pending | All Teams, Executive Leadership
Post-Launch Growth | Gather User Feedback & Iterate Product | 2026-04-17 | 2026-07-31 | Pending | Product Team, Customer Success, Support
| Leverage Initial Users for Referral & Growth Marketing | 2026-05-01 | 2026-10-31 | Pending | Marketing, Sales, Community Manager
| Plan & Initiate Series A Funding Round | 2026-08-01 | 2026-11-30 | Pending | CFO, CEO, Investor Relations
Template Version: 1.0 ¦ Created for Startup Planning - Project Timeline ¦ Last Updated: April 2025