## Worksheet
Startup Planning - Weekly Project Timeline
Week # | Date Range | Phase / Milestone | Key Tasks | Status | Owner(s) | Resources Needed | Risk Level (1-5)
Week 1: Ideation & Validation
W1 | Jan 01 – Jan 07 | Idea Refinement | Finalize core idea, conduct SWOT analysis, validate problem-solution fit. | Pending | CEO, Product Lead |  | 2
W1 | Jan 01 – Jan 07 | User Research Kickoff | Define target audience, create survey questions, recruit initial users. | Pending | Data Analyst, UX Designer |  | 3
Week 2: Market & Competitor Analysis
W2 | Jan 08 – Jan 14 | Competitor Benchmarking | Analyze top 5 competitors, map feature sets, identify gaps. | In Progress | Market Analyst, Product Lead | Competitive analysis tools (e.g., SimilarWeb) | 2
W2 | Jan 08 – Jan 14 | TAM/SAM/SOM Assessment | Evaluate total addressable market size and growth potential. | Pending | Business Analyst, CFO | Industry reports, data APIs | 3
Week 3: MVP Definition & Roadmap Planning
W3 | Jan 15 – Jan 21 | MVP Scope Finalization | Determine must-have features, prioritize based on user value. | Pending | Product Owner, Tech Lead | MVP canvas template | 2
W3 | Jan 15 – Jan 21 | Development Roadmap (Q1) | Create phased timeline with key deliverables and sprints. | Pending | Project Manager, Engineering Lead | Gantt chart tool access | 3
Week 4: Team & Funding Readiness
W4 | Jan 22 – Jan 28 | Tech Stack Selection | Select core technologies and tools for development. | Pending | CTO, DevOps Engineer | Dev stack evaluation matrix | 2
W4 | Jan 22 – Jan 28 | Funding Pitch Deck Draft | Create initial pitch deck with problem, solution, market, and team. | Pending | CFO, Marketing Lead | Design software (Figma/PowerPoint) | 4
Week 5: Prototype & Feedback Loop
W5 | Jan 29 – Feb 04 | Wireframe & Prototype Development | Create low-fidelity wireframes and interactive prototype. | Pending | UX Designer, Frontend Dev | Figma or Adobe XD | 2
W5 | Jan 29 – Feb 04 | User Testing Session (Group A) | Conduct usability testing with 5 target users and collect feedback. | Pending | Product Team, UX Researcher | Testing script, recording tools | 3
Week 6: Finalization & Next Steps Planning
W6 | Feb 05 – Feb 11 | MVP Design Finalization | Refine prototype based on feedback and lock design specs. | Pending | Design Lead, Product Owner | User feedback summary report | 2
W6 | Feb 05 – Feb 11 | Funding & Team Onboarding Prep | Prepare investor outreach materials and initial hire plans. | Pending | CFO, HR Lead | HR templates, pitch deck final version | 4
Total Weeks: 6 ¦ Next Phase: Development & Engineering Kickoff