## Worksheet
Project ID | Project Name | Lead Person | Status | Start Date | End Date | Budget (USD) | Milestone Progress (%)
P001 | Product Development MVP | Alice Johnson | High Risk | 2023-11-01 | 2024-03-15 | $85,000 | 67%
P002 | Market Research & Validation | Robert Chen | In Progress | 2023-10-15 | 2024-01-31 | $25,000 | 89%
P003 | Fundraising Campaign | Sophia Patel | On Track | 2023-12-01 | 2024-05-31 | $150,000 | 43%
P004 | Brand Identity & Website Launch | Marcus Wright | On Track | 2023-11-10 | 2024-02-28 | $35,000 | 96%
P005 | User Acquisition Strategy | Lisa Kim | In Progress | 2024-01-01 | 2024-06-30 | $55,000 | 38%
Total Project Budget (USD) | [6 empty] | $350,000
Note:This analysis view provides an overview of key startup projects. Status indicators reflect current risk and progress levels.
Last updated: April 5, 2024